# Executive Reporting Requirements [Onboarding]

Onboarding Expectations

| Action | Owner | Timing Expectations [>= 80% situations] | Timing Expectations [Worst Case] |
| --- | --- | --- | --- |
| Close Date | Sales Rep | Close Date | Close Date |
| Sales Handoff | Sales Rep | Close Date | 1 Business Day |
| Implementation Manager Assignment | Implementation Leader | 1 Business Day | 2 Business Days |
| Welcome Call | Implementation Manager | 2 Business Days | 4 Business Days |
| Project Plan sent to Customer | Implementation Manager | 2 Business Days | 4 Business Days |
| Data Pull | Implementation Manager | 2 Business Days | 4 Business Days |
| Data in Preview | Data Engineer | See Below |  |
| Training Start | Implementation Manager | See Below |  |
| Data Sign Off | Implementation Manager | See Below |  |
| Travel Scheduled [if relevant] | Implementation Manager | 2 Business Days | 3 Business Days |
| Training Completion | Implementation Manager | See Below |  |
| Go-Live | Implementation Manager | 4 weeks | 6 weeks |
| Customer Success Handoff | Implementation Manager | 6 weeks | 12 weeks |

Reporting Requirements

Every Friday, by 5 pm PT, report on customers who were sold and not yet in CS as of 3 pm PT Friday that day

Report should include:

- Last Meeting Date

- Status of each action above

  - Specific, Actual Date

    - Color coded or flagged if different from baseline timing expectations

    - Additional color code / flag if different from worst case timing expectations

- Forecasted Date

  - For dates that have not yet come to pass

  - Should be in agreement with up-to-date Project Plan

- Customer

- HubSpot link

- Signed agreement link

- Previous Software and/or Data Source details

- MRR

- Implementation Fee

- Active Truck Count

- Specific, actual owners

  - Sales

  - Data

  - Implementation

  - Historical changes in ownership

- Any key special details about the account

- Analytics showing user engagement

  - With the software

  - With the training modules

- Tenant ID

- Links to associated CS and/or data tickets

  - Original date of ticket

  - Target deadline of ticket

  - Actual resolution date of ticket

- Link to Project Plan

- Feature Requests (Savio Links)

- Upsell Opportunities

- AR Status of the Account with Hauler Hero

- Confirmation that customer has been billed and activated revenue tracker updated

- Initial invoiced date (representing when invoice was sent from billing tenant and Activated Revenue sheet was formally updated)

Additional Reporting Views may be needed including but not limited to:

- Monthly Sum of MRR by IM by Welcome Call Date; Go Live Date or CS Handoff Date

- Monthly Sum of Total MRR by all Date Types

- Cohort Breakdown of Total MRR by Date Types for 1 - 2; 3 - 14; 15+ Licenses

- IM Rep Stats

  - Avg Weeks to Implement

  - Avg Months to CS Handoff

  - Avg Truck Count Last 12 Months

  - # Accounts between Assignment and CS Handoff

- Go Live → CS Average Days by Cohort for 1 - 2; 3 - 14; 15+ Licenses

- Rejection Rate over any time period

Project Plan Detail Expectations

- Sent to Customer

  - Within 48 hours of Welcome Call

  - Notification visible to team members and executives in a slack channel or other method

- Accessible by any Hauler Hero team member easily; linked in weekly report

- All key dates and associated owners listed

- Next two weeks of meetings and trainings should always be calendared

  - Send calendar invites after welcome call and continuously thereafter

  - In accordance with Project Plan

  - Continuously updating and adding calendar invites to maintain implementation velocity

- Updated any time new data arises that would cause the go-live to push significantly

  - By more than 2 weeks from the original go-live date

  - Notification visible to team members and executives in a slack channel or other method

Rejection

- Potential Rejections should be flagged in Weekly Reporting

- Rejections will not be factored against expectations listed here if due to:

  - Product gaps

  - Customer situation change

  - Sales error

- Rejections due to process mismanagement should not occur

  - Should be caught by this reporting

  - Management to make resourcing adjustments in real-time based on the data

- Tenant deletion should occur within 40 days of rejection processing

Tenant Hygiene

- Only one tenant per customer

- If additional tenants exist, that should be added to weekly report

  - Reason for additional tenant should be listed

  - Planned deletion date for extra tenant should be listed

Data Sign Off

- Customer should sign off that they have reviewed reports provided by implementation

- This should happen by the time the customer is 60% from the welcome call to the go-live date

  - Worst case, this should happen 80% into the welcome → go-live timeline

  - Delayed data signoffs should be flagged in weekly reporting

- Data signoff document should be linked in the weekly reporting

Go Live

- Defined by customer using HH as primary routing and/or invoicing

  - In certain scenarios, customer might use only one of these

  - In other scenarios, customer might have two different go-live dates for each of these

  - This nuance should be captured in the weekly reporting

- Project Plans should target baseline Go Live Expectations below

| Customer Size | Data Requirements | Go Live Timing Expectations [>= 80% situations] | Go Live Timing Expectations [Worst Case] |
| --- | --- | --- | --- |
| 1 - 2 | Manual | 1 Week | 4 Weeks |
| 1 - 2 | Known Legacy Software | 4 Weeks | 6 Weeks |
| 3 - 14 | Manual | 2 Weeks | 6 Weeks |
| 3 - 14 | Known Legacy Software | 5 Weeks | 8 Weeks |
| 3 - 14 | Evaluation or Custom | 8 Weeks | 12 Weeks |
| 15 - 49 | Known Legacy Software | 8 Weeks | 12 Weeks |
| 15 - 49 | Evaluation or Custom | 12 Weeks | 20 Weeks |
| 50 + | Known Legacy Software | 16 Weeks | 24 Weeks |
| 50 + | Evaluation or Custom | 20 Weeks | 32 Weeks |

Customer Success Handoff

- Date on which Implementation Rep and CS Rep join a call with the Customer

- After this date, all non-support requests should be routed through CS rather than Implementation

- Critical that this happens in a timely fashion so that Implementation can focus on activating new revenue